## Nexus Lab Jira Tracker
Ticket ID | Epic | Project | Task | Priority | Status | Owner | Sprint | Dependency | Output Artifact | Measure of Success | Blockers | Next Action
ASE-R01-A1 | ASE Core Loop | ASE | Design minimal closed-loop architecture (plan→execute→evaluate→refine) | P0 | To Do | SR | Sprint-01 | None | Architecture document | Loop stages clearly defined | Scope ambiguity | Draft architecture flow
ASE-R01-A2 | ASE Core Loop | ASE | Implement planner module prototype | P0 | To Do | SR | Sprint-01 | ASE-R01-A1 | Planner module | Planner generates task sequence | No task schema | Define JSON task schema
ASE-R01-A3 | ASE Core Loop | ASE | Implement evaluator and checkpoint module | P0 | To Do | SR | Sprint-01 | ASE-R01-A2 | Evaluation module | Loop can self-check outputs | Evaluation metrics unclear | Define evaluation metrics
DAF-R01-A1 | Multi-Agent Routing | DAF | Define agent role taxonomy | P0 | To Do | SR | Sprint-01 | None | Agent role map | Roles are bounded and distinct | Too many agent ideas | Limit to 3 agents
DAF-R01-A2 | Multi-Agent Routing | DAF | Implement task router prototype | P0 | To Do | SR | Sprint-01 | DAF-R01-A1 | Routing engine | Tasks routed correctly | Coordination complexity | Prototype simple router
DAF-R01-A3 | Multi-Agent Routing | DAF | Add observability logs for agent actions | P1 | To Do | SR | Sprint-02 | DAF-R01-A2 | Agent logs dashboard | Agent actions visible | No unified logging | Create structured logs
ORA-P01-A1 | ORA Workflow | ORA | Choose one flagship workflow for ORA | P0 | To Do | SR | Sprint-01 | None | Workflow specification | One clear use-case selected | Feature overload | Select one workflow
ORA-P01-A2 | ORA Workflow | ORA | Build memory-assisted assistant prototype | P0 | To Do | SR | Sprint-02 | ORA-P01-A1 | Prototype assistant | Task completed end-to-end | Memory integration incomplete | Connect retrieval layer
ORA-P01-A3 | ORA Workflow | ORA | Integrate tool-use execution layer | P1 | To Do | SR | Sprint-02 | ORA-P01-A2 | Tool orchestration layer | Assistant can execute tools | Execution sandbox missing | Implement isolated execution
SAFE-R01-A1 | Hanuman Shield | Safety | Draft safety refusal and containment policies | P0 | To Do | SR | Sprint-01 | None | Policy document | Unsafe prompts classified | Policy gaps | Write policy rules
SAFE-R01-A2 | Hanuman Shield | Safety | Implement runtime guardrail middleware | P0 | To Do | SR | Sprint-02 | SAFE-R01-A1 | Guardrail middleware | Unsafe actions blocked | No runtime interception | Create middleware layer
SAFE-R02-A1 | Sanjeevani Protocol | Safety | Define rollback and recovery checkpoints | P1 | To Do | SR | Sprint-02 | ASE-R01-A3 | Recovery workflow | System restores from failure | No checkpoint system | Design checkpoint manager
SAFE-R03-A1 | Sudarshan Layer | Safety | Define hard-stop containment conditions | P1 | To Do | SR | Sprint-03 | SAFE-R01-A2 | Containment layer | Unsafe states isolated | Calibration risk | Draft stop-state matrix
MEM-R01-A1 | Memory Core | Anjaneya Memory Resurrection Core | Design memory schema and retrieval graph | P0 | To Do | SR | Sprint-02 | None | Memory schema | Context restored accurately | Schema not finalized | Design graph structure
MEM-R01-A2 | Memory Core | Anjaneya Memory Resurrection Core | Implement memory persistence layer | P0 | To Do | SR | Sprint-03 | MEM-R01-A1 | Persistence engine | Memory survives sessions | Storage architecture pending | Prototype persistence
MEM-R01-A3 | Memory Core | Anjaneya Memory Resurrection Core | Build memory reconstruction pipeline | P1 | To Do | SR | Sprint-03 | MEM-R01-A2 | Reconstruction module | Context restored coherently | Retrieval latency | Optimize retrieval flow
CHP-P01-A1 | Chapie Product | Chapie | Define wedge product use case | P0 | To Do | SR | Sprint-01 | None | Use-case document | Use-case sharply defined | Scope creep | Choose one user pain point
CHP-P01-A2 | Chapie Product | Chapie | Design first user interaction flow | P1 | To Do | SR | Sprint-02 | CHP-P01-A1 | UX flow | User journey understandable | No UX baseline | Create low-fidelity mockup
CHP-P01-A3 | Chapie Product | Chapie | Build first functional demo | P0 | To Do | SR | Sprint-03 | CHP-P01-A2 | Functional demo | Demo completes one workflow | Backend incomplete | Integrate ORA + Memory
VYU-P01-A1 | Founder Intelligence | Cofounder/VyuhaCore | Define clarify-decide-prioritize framework | P1 | To Do | SR | Sprint-02 | None | Decision framework | Founder workflow structured | Ambiguous scope | Formalize framework
VYU-P01-A2 | Founder Intelligence | Cofounder/VyuhaCore | Prototype founder decision dashboard | P1 | To Do | SR | Sprint-03 | VYU-P01-A1 | Dashboard prototype | Tasks and priorities visible | No dashboard infra | Create dashboard UI
AEO-R01-A1 | Aeon Benchmark | Aeon | Select first narrow reasoning benchmark | P1 | To Do | SR | Sprint-03 | None | Benchmark selection | Benchmark measurable | Too many directions | Pick one reasoning domain
AEO-R01-A2 | Aeon Benchmark | Aeon | Prepare dataset slice for benchmark | P1 | To Do | SR | Sprint-03 | AEO-R01-A1 | Dataset subset | Dataset usable for evaluation | Dataset curation incomplete | Create dataset subset
GRI-R01-A1 | Governance Layer | GRIAL | Design governance policy engine | P2 | To Do | SR | Sprint-04 | SAFE-R01-A1 | Policy engine design | Decisions auditable | No integration hooks | Define API interfaces
NXL-R01-A1 | Research Pipeline | Nexus Lab | Create research publication workflow | P1 | To Do | SR | Sprint-04 | None | Publication pipeline | Experiments documented regularly | No standardized process | Design publication template
UNI-R01-A1 | Universal Translator | Universal Translator | Select first translation domain | P2 | To Do | SR | Sprint-05 | None | Translation scope | Reliable narrow translation | Too broad vision | Choose one language pair
MUL-R01-A1 | Multiverse Prototype | Multiverse Detection Prototype | Write one falsifiable hypothesis | P3 | Backlog | SR | Future | None | Hypothesis document | Hypothesis testable | Extreme uncertainty | Define measurable variables