## EMMA Jira Tracker
Ticket ID | Epic | Project | Task | Priority | Status | Owner | Sprint | Dependency | Output Artifact | Measure of Success | Blockers | Next Action
EMM-01-A1 | EMMA Core & Scaffold | EMMA | Establish directories and config loaders | P0 | Complete | SR | Sprint-01 | None | Physical workspace shells & config.py | All folders exist, config loads local model port | None | Setup dev env and .env file | DONE
EMM-01-A2 | EMMA Core & Scaffold | EMMA | Implement FastAPI WebSocket stream server | P0 | Complete | SR | Sprint-01 | EMM-01-A1 | ws_terminal.py WebSocket handler | Client establishes handshake, console receives server pings | WebSocket state handling | Write WebSocket ping-pong loop | DONE
EMM-02-A1 | Metacognitive Loop | EMMA | Build JIT Context Injection manager | P0 | Complete | SR | Sprint-01 | EMM-01-A1 | orchestrator.py context scheduler | Transient tags `<TRANSIENT_CONTEXT>` injected & auto-purged | Token budget estimation | Write regex context insertion script | DONE
EMM-02-A2 | Metacognitive Loop | EMMA | Implement Executor draft generator | P0 | Complete | SR | Sprint-01 | EMM-02-A1 | executor.py draft coordinator | Local model generates structural code proposals | Local model output variance | Optimize execution system prompt formatting | DONE
EMM-02-A3 | Metacognitive Loop | EMMA | Implement Critic stateless AST diff reviewer | P0 | Complete | SR | Sprint-02 | EMM-02-A2 | critic.py AST diff engine | Critic extracts line-level surgical patch blocks | Unclear assertion error formatting | Design standard AST parser mapping | DONE
EMM-03-A1 | Context Compaction | EMMA | Build token monitor and 70% threshold trigger | P0 | Complete | SR | Sprint-02 | EMM-02-A1 | token_prune.py token counter | Compaction loop triggers exactly at 70% max window | Accuracy of local token counter | Implement TikToken or Qwen tokenizer counter | DONE
EMM-03-A2 | Context Compaction | EMMA | Implement local State Vector summarization | P0 | Complete | SR | Sprint-02 | EMM-03-A1 | token_prune.py state-vector compiler | History purged and replaced with 800-token JSON state vector | Model summarization quality | Optimize state vector compression prompts | DONE
EMM-04-A1 | Experience Manifold | EMMA | Setup local vector database and session pool | P0 | Complete | SR | Sprint-02 | EMM-01-A1 | session.py & manifold.py | SQLite / LanceDB table created, reads/writes functional | Local package installation dependencies | Verify LanceDB local storage path
EMM-04-A2 | Experience Manifold | EMMA | Implement semantic similarity retrieval pipeline | P1 | Complete | SR | Sprint-03 | EMM-04-A1 | manifold.py semantic retriever | Prior execution pathways successfully loaded if similarity > 0.85 | Search query latency | Implement local Sentence-Transformers embedding
EMM-05-A1 | Mathematical Safety | EMMA | Write jailed local Python Sandbox subprocess | P0 | To Do | SR | Sprint-01 | EMM-01-A1 | sandbox.py execution jail | Subprocesses run with 256MB RAM cap and 30s timeout limits | Windows job limits mapping | Write OS-specific resource constraints wrapper
EMM-05-A2 | Mathematical Safety | EMMA | Implement GDI alignment index calculator | P0 | To Do | SR | Sprint-02 | EMM-02-A3 | gdi.py scalar calculator | Calculates real-time alignment drift based on semantic & structural signals | Signal weighting calibration | Define baseline weights for α, β, and γ
EMM-05-A3 | Mathematical Safety | EMMA | Implement Sanjeevani rollback gate | P0 | To Do | SR | Sprint-03 | EMM-05-A2 | sahoo_gates.py rollback module | Hard rollbacks cleanly restore previous workspace state if GDI > 0.60 | Directory state locking | Design directory checkpoint snapshot system
EMM-06-A1 | Command Center UI | EMMA | Create React App, navigation, & layout frame | P0 | To Do | SR | Sprint-03 | EMM-01-A1 | React/Vite workspace skeleton & CSS resets | Console renders with dark glassmorphism styling and navigation active | None | Create base dashboard flexbox frame
EMM-06-A2 | Command Center UI | EMMA | Build live WebSocket streaming Terminal widget | P0 | To Do | SR | Sprint-03 | EMM-06-A1 | Terminal.jsx & useWebSocket.js | Real-time streaming agent thoughts show color-coded stages in UI | Auto-scroll terminal buffering | Implement terminal virtualizer hooks
EMM-06-A3 | Command Center UI | EMMA | Integrate Monaco Editor Split Diff viewer | P0 | To Do | SR | Sprint-04 | EMM-06-A1 | DiffViewer.jsx layout component | Side-by-side Monaco diff displays draft edits with colored annotations | Editor load latency in local browser | Setup Monaco editor wrapper and lazy load
EMM-06-A4 | Command Center UI | EMMA | Build SVG GDI speedometer Dial widget | P1 | To Do | SR | Sprint-04 | EMM-06-A1 | DriftDial.jsx and useGDI.js hook | Speedometer dial rotates dynamically in response to GDI WebSocket events | SVG curve animation parameters | Animate arc rotation using react-spring or CSS transitions
EMM-07-A1 | Testing & Deployment | EMMA | Run integration tests on PostgreSQL OAuth integration | P0 | To Do | SR | Sprint-04 | EMM-05-A3 | Integration report & logs | Agent successfully completes integration loop in sandbox, saving 90% tokens | Configuring legacy PostgreSQL server locally | Create mock PostgreSQL Docker server context
EMM-07-A2 | Testing & Deployment | EMMA | Produce video walk-through & compile pitch packages | P1 | To Do | SR | Sprint-04 | EMM-07-A1 | Marp compiled slides, demo video, final code zip | All submission assets finalized and packaged for submission | Demo screen resolution constraints | Verify final submission portal formats